## Slide 1
Millennium Challenge Account Nepal (MCA-Nepal)
Electricity Transmission Project (ETP)
Transmission Line
Activity
Outreach Event, New Delhi

## Slide 2
Electricity Transmission Project
Outcomes:
Add 3,920 MW Tx capacity; reduce losses to 1.9%
Support 3x increase in electricity consumption per capita
Approx. 312 km – 400 kV Tx lines (~857 towers)
3 x 400 kV substations

## Slide 3: Electricity Transmission Line Status
Transmission Line Route Alignment frozen for all five segments
  Lapsiphedi ‐ Ratmate
  Ratmate ‐ New Hetauda
  Ratmate ‐ New Damauli
  New Damauli ‐ New Butwal
  New Butwal ‐ Nepal/India Border
Geotechnical survey works completed
Draft EIA document in advanced stage of preparation

## Slide 4: Electricity Transmission Line Status

## Slide 5
Electricity Transmission Line (Works)
Transmission Lines
400 kV D/C; lots 90-115 km each
3.5 year execution
Design-Build (FIDIC Yellow Book)
Expected launch: Jan 2020
Quality-Price Based Selection
Expected contract sign: Sep 2020

## Slide 6: Segment Wise Physical Information
TL Segments | Physiographic Zone (Length Percentile) |  |  | Elevation (MASL) | 
 | Terai | Siwalik | Middle Mountain | Minimum | Maximum
India Border to New Butwal Substation | 100% |  |  | 100 | 120
New Butwal to New Damauli Substation | 7% | 21% | 72% | 115 | 1380
New Damauli to Ratmate Substation |  |  | 100% | 220 | 1780
Ratmate to New Hetauda Substation |  | 25% | 75% | 410 | 1840
Ratmate to Lapsiphedi Substation |  |  | 100% | 490 | 1918

## Slide 7: Lapsiphedi-Ratmate-New Hetauda 400kV D/C Transmission Line
  Lapsiphedi – Ratmate
  Middle Mountain physiographic zone (Ratmate to Lapsiphedi)
  Section Length : Approx. 59 km
  No. of towers: Approx. 163
  400 kV Quad Moose Double Circuit

## Slide 8: Lapsiphedi-Ratmate-New Hetauda 400kV D/C Transmission Line (contd...)
  Ratmate to New Hetauda
  Middle Mountain zone and partly in Siwalik zone
  Section Length : Approx. 56 km
  No. of towers: Approx. 142
  400 kV Quad Moose Double Circuit
  Possibility of few Quad Moose Quad Circuit towers

## Slide 9: Ratmate-New Damauli 400kV D/C Transmission Line
  Middle Mountain physiographic zone (Ratmate to New Damauli)
  Section Length : Approx. 89 km
  No. of towers: Approx. 251
  400 kV Quad Moose Double Circuit

## Slide 10: New Damauli-New Butwal-Indo Nepal Border 400kV D/C Transmission Line
  New Damauli to New Butwal
  Cuts across three physiographic zones - Terai, Siwalik, and Middle Mountains.
  Section Length : Approx. 90 km
  No. of towers: Approx. 248
  400 kV Quad Moose Double Circuit
  Few Quad Moose Quad Circuit towers near New Butwal substation

## Slide 11: New Damauli-New Butwal-Indo Nepal Border 400kV D/C Transmission Line
  New Butwal to India Border
  Terai physiographic zone
  Section Length : Approx. 18 km
  No. of towers: Approx. 52
  400 kV Quad Moose Double Circuit

## Slide 12: Transmission Line Towers
Probable Tower Types
Suspension
Tension (mostly)
Special Tower (for long spans)
Multi Circuit (for corridor issues)

## Slide 13: Access Road Classification
Category | Width | Turn radius | Slope percent | Remarks
1 | ~5m | min. 90 ft | 0 to 15 | Generally paved or unpaved and well maintained
2 | ~3m | Min. 45 ft | 0 to 30 | Unpaved road in fair condition
3 | ~2.5m | Min. 20 ft | 0 to 45 | Unpaved narrow road in poor condition
4 | ~1.5m | Min. 15 ft | 0 to 45 | Wide trail in fair condition
5 | ~0.5m-1m | Min. 6ft | 0 to 24 | Narrow trail.
6 |  |  |  | Aerial access in the only option

## Slide 14: Transmission Line Preliminary Assessment of Road Access
Length of Access Roads per Category in each Segment |  |  |  |  | 
Segment | Road Category (in km) |  |  |  | 
 | 1 | 2 | 3 | 4 | 5
New Butwal to India Border | 49.0 | 22.2 | 12.4 | 8.8 | 
New Butwal to New Damauli | 216.2 | 86.0 | 115.1 | 41.1 | 45.2
New Damauli to Ratmate | 201.5 | 32.4 | 156.7 | 126.8 | 61.2
Ratmate to Lapsephedi | 21.1 | 65.6 | 97.3 | 57.3 | 25.9
Ratmate to New Hetauda | 187.6 | 96.6 | 52.9 | 29.7 | 28.5

## Slide 15: Resettlement and Land Acquisition
Resettlement policy framework completed
Entitlement Matrix completed
RAP of Transmission lines will be completed by June 2020
Land compensation payment to be completed by December 2020

## Slide 16: Challenges
Difficult Terrain, Transportation of materials: Elevations vary from 100 meters (330 ft.) to around 2000 meters (6563 ft.)
Land acquisition and securing right of way
Heavy monsoon season of 3 months (9 months effective in a year)
Forest clearance
Major river crossing
  Trishuli
  Kali Gandaki
  Seti

## Slide 17: Expected Timeline
Activities | 2020 |  |  |  |  |  |  |  |  |  |  |  | 21 | 22 | 23 | 24 |  | 25
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  |  | Jun | Jul | Jun
Bid Release (in web & Newspaper) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Site visit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-bid meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Bid Submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Technical Bid opening |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Financial Bid Opening |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Award of contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Construction Period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Defect Notification Period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 18: MCA Partnership program
A benefit sharing component of ETP
Intent: Benefits from infrastructure development are equitably shared with people directly and indirectly affected by the project which goes beyond compensation and mitigation measures

## Slide 19: Thematic Areas
Thematic Area 1: Extension and upgrading of grid-based electricity distribution system
Thematic Area 2: Provision of off-grid electricity solutions
Thematic Area 3: Provision of capacity building support to increase benefits of electricity

## Slide 20: MCA Partnership program Status
Framework developed
Sub-activity consultation to be done by December 2019
Expected date for construction bid release for thematic area 1 by August 2020
Expected date for Request for proposal for Thematic area 2 and 3 by March 2020

## Slide 21
Environmental and Social Issues in Transmission Line

## Slide 22: Environmental and Social Impacts of TL
Land needs to be acquired for transmission towers – private land or forest.
Restriction on the use of row land – 46m, 23m on each side.
Landslides/soil erosion
Health and safety issues
Trafficking in person

## Slide 23: MCA - Nepal / MCC Policies
Follow GoN rules and regulations including Land Acquisition Act, Environment Protection Act, and Regulations, Forest Acts.
Follow MCC Environmental Guidelines and International Finance Corporation (IFC) Performance Standards on Environmental and Social Sustainability.
Follow MCC Gender Policy and Social and Gender Integration Guidelines.

## Slide 24: Additional Employer’s Requirements of Note
Respect IFC Performance Standards
Respect environ. & social clauses
Abide by health & safety plans
Engage with stakeholders
Gender & Social Inclusion Plan

## Slide 25: Avoidance (Examples)
Avoid biodiversity hotspots
Avoid settlements
Avoid cultural heritages

## Slide 26: Minimize (Examples)
Minimize forest clearance by appropriate tower designs, use of pilot wire, drones, etc. for stringing.
Minimize the need for access roads by use of porters and other methods.

## Slide 27: Mitigate (Examples)
Use of bird diverters
Reforestation
Slope stabilization/rehabilitation works

## Slide 28: For more Information
MCC-funded business opportunities, please visit:
www.mcc.gov/work-with-us
For MCA-Nepal business opportunities, please visit:
www.mcanp.org
For Q&A regarding the procurement, please contact:
info@mcanp.org

## Slide 29
Thank you.